## Meth Test 001
Meth Clothing Website Test Module
Test Case ID |  | Meth 001 | Test Case Description | Review and Test for fulfillment of User Story 1: 'Website Design'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for expected Basic requirements for a functional website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested | 2020-02-24 |  | Test Case (Pass/Fail/Not Executed) |  | Fail
|  |  | Date of Re-Testing | February 28, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 4.1.1 | Blank Fields
|  |  |  | 4.2.1 | First Name: Paul, Last Name: W, E-Mail Address: G00375061@gmit.ie, Password: 12345 Password Confirm: 12345
Test Scenario | Check website appearance and current functionality
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass / Fail / Suspended
1 | Open website from Html 'Index' File (Pre-Release access - URL later) |  | Site should open | As Expected. |  |  | Pass |  | PASS
1.1 | Visual assessment |  | Check for pleasing appearance with use of product images and possibly a carousel to display products. | As Expected. Good use of the carousel. |  |  | Pass ( but recommend addition of 'Meth Clothing' banner at the top of the page somewhere? The only place the company name is vivsible is in the Copyright text at the bottom of the page). |  | PASS
2 | Top Menu Bar |  | Present | Present with Home Page/About Us/Shop(w/Dropdown)/Cart options already available, so tested below. |  |  | Pass |  | PASS
2.1 | Home Page' button Test |  | To return to Home Page from all pages. | As Expected |  |  | Pass |  | PASS
2.2 | 'About Us' button Test |  | To go to 'About Us' Page | ERR_FILE _NOT-FOUND |  |  | Fail (but not specified in this User story anyway)
2.3 | 'Shop' button Test |  | Dropdown 'Shop' Menu | Dropdown menu present, currently with one option: 'Cloths'. As expected but typo! |  |  | Fail (small typo) 'Clothes' NOT cloths. |  | PASS
2.4 | 'Cart' button Test |  | Access to Shopping Cart. | As expected, but following typos: 'Shopping' NOT 'Shipping'. Uppercase C for 'cart'. 'Continue' NOT 'Continiu'. |  |  | Fail (minor typos) |  | PASS
3 | 'Clothes' button present via 'Shop' button, so Test for functionality. |  | Access to 'Clothes' page | As expected. (Additional 'Login' and 'Register' buttons noted on Top Menu Bar.) |  |  | Pass |  | PASS
3.1 | Re-Test Functionality of Buttons on Top Menu Bar from Clothes Page |  | Should function as previously in Steps 2.1, 2.2, 2.3 | Same functionality, but 'Clothes' button dropdown menu now has two additional, irrelevent(?) options ('Sports' and 'Accessories'). |  |  | Fail (Additional options from 'Clothes' dropdown menu need to be removed) |  | PASS
4 | As 'Login' and 'Register' buttons now appear in Top Menu Bar, will test these for correct functionality. |  | - | - |  |  | - |  | -
4.1 | 'Login' Button Test |  | Expect pop-up for entry of Login Details | As expected. (Pop-up entry box for e-mail address and password to login plus two further buttons, one to confirm entry of Login details, one to Register if not currently registered).However, 'Register' button not active. |  |  | Failed (Need to activate a link to the Register page from the 'Register' button that appears in Login Pop-up.) |  | Suspended/Removed (No User Story)
4.1.1 | Test 'Login' Button that appears in pop-up following previous 'Login' button activation for unregistered user |  | Expect Error/Invalid or similar. | As expected. Pop-up stating Username or Password invalid, Try Again and 'OK' button to return to 'Login' pop-up box. (Note: Slight inconsistency with use of 'E-Mail Address' in Login pop-up and Invalid 'Username' in Error pop-up.) |  |  | Pass |  | Suspended/Removed (No User Story)
4.2 | Test 'Register' Button that appears in pop-up follwing 'Login' button activation in 4.1 above. |  | Expect Pop-up Form or link to Registration Page for input of user details. | As expected. Pop-up with entry requirements (First Name,Last Name, E-Mail Address, Password, Password Confirmation) plus 'Register' button for submission. |  |  | Pass |  | Suspended/Removed (No User Story)
4.2.1 | Test 'Register' Button in Pop-up having entered a set of Test details into the form. |  | Expect confirmation of registration Pop-up | Pop-up confirming successful Registration with details submitted in form. Small typo here, should be 'registered' NOT 'registred'. |  |  | Pass |  | Suspended/Removed (No User Story)
4.2.2 | Re-Test 4.2.1 with fields left blank in Registration form. |  | Expect Error/Invalid or similar. | Pop-up requesting missing fields to be filled plus 'OK' button to return to form. |  |  | Pass |  | Suspended/Removed (No User Story)
4.2.3 | Re-Test 4.2.2 with all scenarios for field completion/non-completion before submission |  | Expect confirmation for correct completion of form and Error if form incomplete. | All scenarios function correctly except when leaving the Password Confirmation' field blank having filled the other fields. This results in a confirmation for correct completion which is incorrect. |  |  | Fail (Should get the Pop-up requesting missing fields to be filled if Password Confirmation is left blank) |  | Suspended/Removed (No User Story)
4.3 | Test for successful Login by a Registered User. |  | Expect confirmation of successful Login on entry of Registered user. | As expected. Pop-up message acknowledging successful Login. Also, change of 'Login' button on Top Menu Bar to 'Logout'. |  |  | Pass |  | Suspended/Removed (No User Story)
4.3.1 | Test new 'Logout' button for correct functionality. |  | Expect button to revert to 'Login' on click. | As expected. |  |  | Pass |  | Suspended/Removed (No User Story)
5 | Secondary Menu Bar present so will test functionality |  |  | Has four buttons of 'Free Shipping on Orders over €50','Free Returns', 'Facebook', 'Instagram' available.
5.1 | Test 'Free Shipping on orders over €50' button for functionality and relevence. |  | Expect either link to more detailed description of offer or no button functionality at all, just a notification/banner. | Unexpected link to DPD Shipping website. |  |  | Fail. Suggest either remove button functionality or provide link to more detailed description of Free Shipping offer. This would usually be dealt with in the Shopping Basket? |  | PASS
5.2 | Test 'Free Returns' button for functionality and relevence. |  | Expect either link to more detailed description of offer or no button functionality at all, just a notification/banner. | Unexpected link to DPD Shipping website. |  |  | Fail. Suggest either remove button functionality or provide link to more detailed description of Free Shipping offer. This would usually be dealt with in the Shopping Basket? |  | PASS
5.3 | Test 'Facebook' button for functionality and relevence. |  | Expect link to 'Meth Clothing' Facebook page. | Link to Facebook main login page. |  |  | Pass. Useful feature if the PO wishes to add a link to Meth Clothing Facebook page at a later date. |  | PASS
5.4 | Test 'Instagram' button for functionality and relevence. |  | Expect link to 'Meth Clothing' Instagram page. | Link to Instagram main login page. |  |  | Pass. Useful feature if the PO wishes to add a link to a Meth Clothing Instagram page at a later date. |  | PASS

## Meth Test 002
Meth Clothing Website Test Module
Test Case ID |  | Meth 002 | Test Case Description | Review and Test for fulfillment of User Story 2: '…...browse products on offer'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested | 2020-02-24 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome)
Test Scenario | Verify that on clicking 'Clothes' button from 'Shop' dropdown Menu that user can browse items of clothing on offer
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Open website from Html 'Index' File, Click on Shop in Top Menu Bar, Click on Clothes button from dropdown menu. |  | Page should open with selection of Clothing on offer, including images (and possibly pricing) | As Expected. Selection of Clothing displayed with prices and option to add to basket. No size selection, but not a requirement for this Sprint. |  |  | Fail (The God Father? Should it not be The Godfather?) |  | PASS
2 | Add to Cart buttons available for each product so will test functionality |  | On click item should be added to Shopping Cart with associated price | When 'Add To Cart' button is clicked, a pop-up dialog appears to indicate successful addition to cart. |  |  | Pass |  | PASS
2.1 | Check that item is actually in Shopping Cart following previous test. |  | When Cart button is clicked in Top Menu Bar, the Cart should be displayed with item in it. | Item appears in Shopping Cart with image, product name and price displayed. Also an increment/decrement button to change the quantity, a Trash (Delete) button and an 'Update Shopping Cart' button. |  |  | Pass |  | PASS
2.2 | Check functionality of increment/decrement button in shopping Cart. |  | Increase quantity of item / Decrease quantity of item. | As Expected. |  |  | Pass |  | PASS
2.3 | Check functionality of 'Update Shopping Cart' button. |  | Update Total Price with increased/decreased quantities. | As Expected. |  |  | Pass |  | PASS
2.4 | Check functionality of 'Trash' button. |  | Delete items fom Shopping Cart with 'Trash' button. | As expected. |  |  | Pass |  | PASS
3 | Test Checkout button to exit Shopping Cart and pay for goods etc. |  | On clicking Checkout button, exit Shopping Cart and open Payment/Delivery Details page, if coded. | Exits Shopping Cart as expected and clears items, but payment etc is not in this Sprint. |  |  | Pass |  | PASS

## Meth Test 003
Meth Clothing Website Test Module
Test Case ID |  | Meth 003 | Test Case Description | Review and Test for fulfillment of User Story 3: 'Owner wants a Discount for products'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested | 2020-02-28 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1 | Coupon: 'discount10'
Test Scenario | Verify that on adding Coupon Code to Coupon Code Input Form and clicking 'Use Coupon' button, that appropriate discount is applied and Total Price updated.
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Add Items to Shopping Cart using 'Add To Cart' button on Clothes page. Go into Shopping Cart, add Hard Coded Coupon 'discount10' to Coupon Code input form, Click 'Use Coupon' button to apply discount. |  | Expect Total Price to be reduced by 10% and updated accordingly. | As Expected, discount is correctly applied and Total Price updated correctly. Note placeholder typo where 'Coupon Code' is mispelt as 'cupone code', Also same typo on 'Use Coupon' button. |  |  | Fail. Typos only |  | PASS

## Meth Test 004
Meth Clothing Website Test Module
Test Case ID |  | Meth 004 | Test Case Description | Review and Test for fulfillment of User Story 'Care Instructions'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested | 2020-03-10 |  | Test Case (Pass/Fail/Not Executed) |  | PASS
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario | Check for display of Clothing Care Instructions (ie Washing tempersture etc.)
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Open Clothes page and check for display of Care Instructions such as washing machine water temperature. |  | Expect Care Instructions to appropriately displayed. | As Expected. |  |  | PASS. |  | -

## Meth Test 005
Meth Clothing Website Test Module
Test Case ID |  | Meth 005 | Test Case Description | Review and Test for fulfillment of User Story 'Feedback Page'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested |  |  | Test Case (Pass/Fail/Not Executed)
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Select 'Feedback' option. |  | A Feedback form to take customer details and feedback. | As Expected. |  |  | PASS |  | -

## Meth Test 006
Meth Clothing Website Test Module
Test Case ID |  | Meth 006 | Test Case Description | Review and Test for fulfillment of User Story 'Is Item in Stock?'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested |  |  | Test Case (Pass/Fail/Not Executed)
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 |  |  |  | A Expected. |  |  | PASS |  | -

## Meth Test 007
Meth Clothing Website Test Module
Test Case ID |  | Meth 007 | Test Case Description | Review and Test for fulfillment of User Story 'Links to Social Media websites'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested |  |  | Test Case (Pass/Fail/Not Executed)
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Reference Step # 5.3 in Meth Test 001 - Check Button has been Re-Activated and functions correctly as before. |  | Expect link to 'Meth Clothing' Facebook page. | Link to Facebook main login page. |  |  | PASS. Can be edited to link to Meth Clothing Facebook page directly when created at a later date. |  | -
2 | Reference Step # 5.4 in Meth Test 001 - Check Button has been Re-Activated and functions correctly as before. |  | Expect link to 'Meth Clothing' Instagram page. | Link to Instagram main login page. |  |  | PASS. Can be edited to link to Meth Clothing Instagram page directly when created at a later date.

## Meth Test 008
Meth Clothing Website Test Module
Test Case ID |  | Meth 008 | Test Case Description | Review and Test for fulfillment of User Story 'Responsive Layout for different devices'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested |  |  | Test Case (Pass/Fail/Not Executed) |  | PASS
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Check in code (for each page) for availability of drop-down menu for selection of various devices for which to scale website |  | Website scaled appropriately for device selected. | As Expected. |  |  | PASS. |  | -

## Meth Test 009
Meth Clothing Website Test Module
Test Case ID |  | Meth 009 | Test Case Description | Review and Test for fulfillment of User Story 'Update Quantities'
Created By |  | Paul | Reviewed By | Walter |  | Version |  | 1.0
Test Title : |  | Check for ability to browse products on offer on website |  |  |  | Test Designed by : |  | Paul
Tester's Name |  | Paul | Date Tested |  |  | Test Case (Pass/Fail/Not Executed) |  | PASS
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Browser (Google Chrome) |  |  | 1
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended |  | Re-Test - Pass/Fail
1 | Check for correct quantity updates when items selected. |  | Quantities and Total Price updated correctly when various numbers of items selected for purchase. | As Expected. |  |  | PASS. |  | -